## Sheet1
Area | Challenges | Lessons Learnt | Mitigations / Solutions | Field
Chemical Compatibility & Water Treatment. | Sensitivity of alkaline formulations to divalent ions and added complexity of offshore water softening; desalination increased weight and operational load. | Offshore implementation depends on chemical compatibility with seawater; water treatment units significantly impact CAPEX and topside weight. | Introduce seawater-tolerant alkaline formulations (e.g., OA-200) to simplify operations and adopt seawater-compatible chemicals to reduce or eliminate extensive softening requirements. | Angsi
Chemical Validation | Lab results needed confirmation in field conditions | Laboratory performance alone cannot guarantee field success | Conduct pilot field tests (e.g., SWCT) to validate lab findings and guide final chemical selection | Angsi
Chemical Cost & Logistics | High cost and large storage volume required offshore | Offshore chemical handling and storage are major cost drivers | Shift blending onshore and optimize formulations to enhance cost efficiency and streamline logistics | Angsi
Facilities & Infrastructure | CEOR vessel design exceeded weight expectations | Early design assumptions often underestimate EOR facility footprint | Employ modular, compact designs and move some processing onshore to minimize weight and cost | Angsi
Fluid Handling & Pumping Systems | High-concentration injected fluids caused elevated pressure and pumping difficulties; handling mixed oil-water-gas phases offshore added complexity. | Reliable and efficient multiphase flow management is critical for stable offshore CEOR operations. | Deploy twin-screw or high-torque multiphase pumps designed for chemical injection and mixed-phase flow to maintain pressure control and operational stability. | Angsi
Simulation & Risk Management | Uncertainty in Sor, adsorption, and IFT performance | Static and dynamic uncertainty integration is key to de-risking full-field EOR | Utilize probabilistic modeling and pilot testing for performance validation and uncertainty reduction | Angsi